## CI Plan
Activities | Resource | Status | Start Date | End Date | Planned Effort | Key Dependencies (Owner) & Assumptions
Pre-requisites
Virtual Machines Procurement | FPL Infra/Server Team | Not Started | 2016-08-17 | 2016-08-18 |  | Infrastructure for Cloudset & SONAR setup has to be given by FPL with all network & access privileges (1 VM for CloudSet & 1 VM for SONAR)
Build Environment and Deployment environment with all necessary middleware and network connectivity | FPL Infra/Server Team | Not Started | 2016-08-17 | 2016-08-18 |  | Has to be shared by FPL
IBM RTC URL and Access Control | FPL Infra/Server Team | Not Started | 2016-08-17 | 2016-08-18 |  | Customer already has license for RTC and its pre-installed & Configured
IBM Udeploy URL and Access Control | FPL Infra/Server Team | Not Started | 2016-08-17 | 2016-08-18 |  | Customer already has license for IBM Udeploy and its pre-installed & Configured
Admin Rights to Udeploy & RTC for orchestration | FPL Infra/Server Team | Not Started | 2016-08-17 | 2016-08-18 |  | Has to be shared by FPL
FPL LDAP/ SMTP Details | FPL Infra/Server Team | Not Started | 2016-08-17 | 2016-08-18 |  | Has to be shared by FPL (For CloudSet authentication & send mails from CloudSet)
Cloudset Installation | Cognizant GTO Team | Not Started | 2016-08-19 | 2016-08-22
SONAR Installation | Cognizant GTO Team | Not Started | 2016-08-23 | 2016-08-23
MongoDB Installation & Integration with Cloudset | Cognizant GTO Team | Not Started | 2016-08-24 | 2016-08-24 |  | MongoDB is used to store failure cause information in CloudSet
MYSQL DB Installation & Integration with SONAR | Cognizant GTO Team | Not Started | 2016-08-24 | 2016-08-24 |  | MySQL is used as back-end for SONAR
Cloudset/SONAR/IBM Udeploy necessary Plug-in/Software installation & Validation | Cognizant GTO Team | Not Started | 2016-08-25 | 2016-08-25 |  | Install required plugins for CloudSet & uDeploy & SONAR
CI Dev Build Pipeline Setup
Understand Java Project & Validate the appropriate ANT Goals | Cognizant GTO Team | Not Started | 2016-08-26 | 2016-08-29 |  | FPL Account team will share the FPL.COM project with complete code (APP & DB), fully automated Build Script with Automated Unit Test & Coverage instrumentation, Any issues on Build Script / JUnit etc. has to be owned by application team
Configure SMTP & Authentication in Cloudset | Cognizant GTO Team | Not Started | 2016-08-30 | 2016-08-30
Cloudset - JDK,ANT Configuration | Cognizant GTO Team | Not Started | 2016-08-31 | 2016-09-01
Cloudset - Check Out, Compile and packaging | Cognizant GTO Team | Not Started | 2016-08-31 | 2016-09-01
Cloudset - Unit Test result Configuration | Cognizant GTO Team | Not Started | 2016-08-31 | 2016-09-01
Cloudset - Unit Test Quality Gate Configuration | Cognizant GTO Team | Not Started | 2016-08-31 | 2016-09-01
Cloudset - SONAR Integration | Cognizant GTO Team | Not Started | 2016-09-02 | 2016-09-05
Cloudset - SONAR Quality Gate / Build Breaker / Threshold Configuration | Cognizant GTO Team | Not Started | 2016-09-02 | 2016-09-05
Onboarding FPL.COM Project in to the Build Pipeline using Self-Service feature provided by Cloudset for the existing repository | Cognizant GTO Team | Not Started | 2016-09-06 | 2016-09-08
CI Dev Integration Test Pipeline Setup
Cloudset - ANT - Selenium Integration Testing Setup | Cognizant GTO Team | Not Started | 2016-09-09 | 2016-09-09
Cloudset - Post Build Script Quality gate based on Selenium Integration Test Results | Cognizant GTO Team | Not Started | 2016-09-12 | 2016-09-12
Cloudset & Udeploy Integration
Installing agents from the IBM UrbanCode Deploy server and mapping it to resources | Cognizant GTO Team | Not Started | 2016-09-13 | 2016-09-13
Integrate UrbanCode Deploy with Cloudset | Cognizant GTO Team | Not Started | 2016-09-14 | 2016-09-20
Create Application,Component , Environemnt and process | Cognizant GTO Team | Not Started | 2016-09-14 | 2016-09-20
IBM UrbanCode WebSphere Application Server and Middleware Configuration | Cognizant GTO Team | Not Started | 2016-09-14 | 2016-09-20
Deploy application into IBM WAS server | Cognizant GTO Team | Not Started | 2016-09-14 | 2016-09-20
Validation & Demo
Validating the end to end Dev Pipeline | Cognizant GTO Team | Not Started | 2016-09-14 | 2016-09-20
Demo | Cognizant GTO Team | Not Started | 2016-09-21 | 2016-09-21 |  | No license cost for Cloud Set during POC. On Completion of POC Cloudset will be uninstalled
Note :-Any deviation / additional work / change in scope will result in additional / change in effort