## Sheet1
S.NO | Activity | Revised Start Date | Revised End Date | Owner | Actual Start Date | Actual End Date | Blockers | Remarks | Status
1 | Validation of Virtual Assist hosted in AWS
2 | Installation and configuration of self-service toolset |  |  |  | 2016-12-26 | 2016-12-27
2.1 | Install and configure Jenkins |  |  |  | 2016-12-26 | 2016-12-26
2.2 | Install and configure JIRA |  |  |  | 2016-12-26 | 2016-12-27
2.3 | Install and configure GitLab |  |  |  | 2016-12-27 | 2016-12-27
3 | Opening firewall request from GTO SEA Datacenter to AWS |  |  |  | 2016-12-26 | 2016-12-28
3.1 | Identify the server ip of the source and target systems |  |  |  | 2016-12-26 | 2016-12-26
3.2 | Create a firewall request |  |  |  | 2016-12-26 | 2016-12-28
4 | Configuring the reverse proxy configuration for Virtual Assist to communicate with self-service tools. |  |  |  | 2016-12-27 | 2016-12-28
4.1 | Identify the server to host apache web server |  |  |  | 2016-12-27 | 2016-12-27
4.2 | Install and configure apache server |  |  |  | 2016-12-27 | 2016-12-27
4.3 | Create a reverse proxy request to expose the apache url to internet |  |  |  | 2016-12-27 | 2016-12-27
4.4 | Create the necessary configuration to route each request from the Virtual Assist to self-service applications |  |  |  | 2016-12-27 | 2016-12-28
5 | Create the necessary jobs in Jenkins |  |  |  | 2016-12-28 | 2016-12-28
5.1 | Create template job in Jenkins for Branch Build pipeline |  |  |  | 2016-12-28 | 2016-12-28
5.2 | Create template job in Jenkins for Branch merge request creation |  |  |  | 2016-12-28 | 2016-12-28
5.3 | Create admin job in Jenkins to orchestrate the template jobs |  |  |  | 2016-12-28 | 2016-12-28
5.4 | End to end testing of the configured jobs |  |  |  | 2016-12-28 | 2016-12-28
6 | Virtual Assist interaction with self-service applications. |  |  |  | 2016-12-28 | 2016-12-29
6.1 | Sharing the application endpoint with the Virtual Assist team. |  |  |  | 2016-12-28 | 2016-12-28
6.2 | Testing the self-service application connectivity from Virtual Assists and validating the response |  |  |  | 2016-12-28 | 2016-12-29
6.3 | Defining the Virtual Assist chat text content for each use case. |  |  |  | 2016-12-29 | 2016-12-29
7 | Final Demo & Next Steps |  |  |  | 2016-12-30 | 2016-12-30